## project plan
WBS ID | Phase | Task | Task Description | Story Summary | Story Points | Dependency (Predecessor) | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | CPM
1.1 | Discovery | Scope Definition | Confirm in-scope courts languages exclusions(outside of EI-Jurisprudence) and definition of done | Confirm scope and success criteria | 5 |  | X | [5 empty] | YES
1.2 | Discovery | Scope Validation | Compare Feature sets in EVA DA vs Jurisprudence | Validate jurisprudence sources and access | 8 | 1.1 | X | [5 empty] | YES
1.3 | Discovery | Source Validation | Validate CanLII API and court site access patterns limits and availability | Assess data quality risks | 5 | 1.2 | X | [5 empty] | NO
1.4 | Discovery | Data Quality Assessment | Identify unparsable PDFs missing bilingual pairs and inconsistencies | Confirm EVA DA constraints | 8 | 1.1 | X | [5 empty] | NO
1.5 | Discovery | EVA DA Capability Assessment | Confirm ingestion indexing filtering citation and UI constraints | Confirm governance posture | 5 | 1.1 |  | X |  |  |  |  | YES
2.1 | Design | CDC Design | Design change detection strategy timestamps identifiers and refresh cadence | Design CDC strategy | 8 | 1.5 |  | X |  |  |  |  | YES
2.2 | Design | Download Strategy Design | Design PDF HTML retrieval retries backoff and error handling | Design download strategy | 5 | 2.1 |  | X |  |  |  |  | YES
2.3 | Design | Metadata Schema Design | Define metadata required for filtering citations and traceability | Define metadata schema | 8 | 1.3 |  | X |  |  |  |  | YES
2.4 | Design | Storage Contract Design | Define folder structure naming conventions and overwrite rules | Define storage contract | 5 | 2.3 |  | X |  |  |  |  | YES
2.5 | Design | Design Semantic Search Feature | Design and start coding for semantic search | Design EVA DA indexes | 8 | 1.4 |  |  | X |  |  |  | NO
2.6 | Design | Data Ingestion : Part 2 | Query and Summary design to replicate current ingestion patter | Design prompts and UX rules | 5 | 2.5 |  |  | X |  |  |  | NO
3.1 | Build | CDC Job Implementation | Implement scheduled job detecting new and updated cases | Implement CDC job | 8 | 2.1 |  |  |  | X |  |  | YES
3.2 | Build | Document Downloader Implementation | Implement resilient EN FR PDF HTML downloader | Implement document downloader | 8 | 2.2 |  |  |  | X |  |  | YES
3.3 | Build | Metadata Generation Implementation | Generate structured metadata for each document | Implement metadata generator | 8 | 2.3 |  |  |  | X |  |  | YES
3.4 | Build | Storage Provisioning | Provision ingestable storage paths and access controls | Provision storage paths | 6 | 2.4 |  |  |  | X |  |  | YES
4.1 | Integration | Project Space Creation | Create EVA DA project space for EI Jurisprudence | Create jurisprudence project | 3 | 2.5 |  |  |  |  | X |  | NO
4.2 | Integration | Index Creation | Create and configure EN and FR jurisprudence indexes | Create EN/FR indexes | 5 | 4.1 |  |  |  |  | X |  | NO
4.3 | Integration | Indexer Configuration | Configure indexers chunking embeddings and schedules | Configure indexers | 8 | 3.4 |  |  |  |  | X |  | YES
4.4 | Integration | Filter Enablement | Enable court and language filters using metadata | Enable court filters | 5 | 3.3 |  |  |  |  | X |  | NO
4.5 | Integration | Citation Enforcement | Ensure citation metadata is passed and enforced in responses | Enforce citations | 5 | 2.6 |  |  |  |  | X |  | NO
4.6 | Integration | Feedback Capture Enablement | Enable thumbs up down and comment logging | Enable feedback capture | 5 | 2.6 |  |  |  |  | X |  | NO
5.1 | Test | Data Validation | Validate coverage per court language and citation accuracy | Validate data coverage & citations | 8 | 4.3 | [5 empty] | X | YES
5.2 | Test | Functional Testing | Test in-scope out-of-scope behavior filters and UX | Functional testing | 8 | 4.4 | [5 empty] | X | NO
5.3 | Test | Performance Testing | Validate indexing time query latency and error rates | Performance testing | 5 | 4.3 | [5 empty] | X | NO
5.4 | Test | Tuning and Remediation | Adjust chunking prompts retries thresholds | Tuning and fixes | 5 | 5.2 | [5 empty] | X | NO
6.1 | Deployment | UAT Deployment | Deploy jurisprudence capability to EVA DA UAT | UAT deployment | 5 | 5.1 | [5 empty] | X | YES
6.2 | Deployment | Operational Runbook | Document extraction re-runs exceptions and support model | Produce runbook | 3 | 3.1 | [5 empty] | X | NO
6.3 | Deployment | Soft Launch Monitoring | Monitor usage review feedback and capture backlog | Soft launch monitoring | 3 | 6.1 | [5 empty] | X | NO
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CDC = Change Data Capture… A controlled mechanism to detect, retrieve, and process only new or changed jurisprudence documents since the last run — instead of re-ingesting everything.

## Epic, Stories
Issue Type | Epic Name | Summary | Description | Sprint
Epic | EPIC-01 Discovery & Alignment | Discovery and Alignment | Lock scope sources governance and EVA DA constraints for jurisprudence integration | Sprint 1
Story | EPIC-01 Discovery & Alignment | Confirm scope and success criteria | Confirm in-scope courts languages exclusions and definition of done | Sprint 1
Story | EPIC-01 Discovery & Alignment | Validate jurisprudence sources and access | Validate CanLII API usage court site access patterns and rate limits | Sprint 1
Story | EPIC-01 Discovery & Alignment | Assess data quality risks | Identify unparsable PDFs missing bilingual pairs and document risks | Sprint 1
Story | EPIC-01 Discovery & Alignment | Confirm EVA DA constraints | Confirm ingestion indexing filtering citation and UI constraints in EVA DA | Sprint 1
Story | EPIC-01 Discovery & Alignment | Confirm governance posture | Confirm public data classification logging retention and no new SAA boundary | Sprint 2
Epic | EPIC-02 Design Extraction & Metadata | Design extraction and metadata | Produce build-ready designs for CDC extraction metadata storage and prompts | Sprint 2
Story | EPIC-02 Design Extraction & Metadata | Design CDC strategy | Define change detection logic timestamps identifiers and run frequency | Sprint 2
Story | EPIC-02 Design Extraction & Metadata | Design download strategy | Define PDF HTML download retries backoff and exception handling | Sprint 2
Story | EPIC-02 Design Extraction & Metadata | Define metadata schema | Define case court language dates URLs and citation fields | Sprint 2
Story | EPIC-02 Design Extraction & Metadata | Define storage contract | Define folder structure naming conventions and overwrite rules | Sprint 2
Story | EPIC-02 Design Extraction & Metadata | Design EVA DA indexes | Define EN FR index strategy chunking and filters | Sprint 3
Story | EPIC-02 Design Extraction & Metadata | Design prompts and UX rules | Define scope enforcement citation enforcement and feedback wording | Sprint 3
Epic | EPIC-03 Build Extraction Pipeline | Build extraction pipeline | Implement CDC downloader metadata generation and storage | Sprint 4
Story | EPIC-03 Build Extraction Pipeline | Implement CDC job | Build scheduled job to detect new and updated cases via CanLII | Sprint 4
Story | EPIC-03 Build Extraction Pipeline | Implement document downloader | Build resilient EN FR downloader with retries and logging | Sprint 4
Story | EPIC-03 Build Extraction Pipeline | Implement metadata generator | Generate structured metadata enabling filters and citations | Sprint 4
Story | EPIC-03 Build Extraction Pipeline | Provision storage paths | Create ingestable storage structure for raw docs and metadata | Sprint 4
Epic | EPIC-04 EVA DA Configuration & Integration | Configure EVA DA | Create indexes configure ingestion filters citations and feedback | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Create jurisprudence project | Create EVA DA project space for EI Jurisprudence | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Create EN FR indexes | Create and validate jurisprudence EN and FR indexes | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Configure indexers | Configure indexers chunking and embeddings | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Enable court filters | Implement court and language filters using metadata | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Enforce citations | Ensure citation metadata is passed and enforced in prompts | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Enable feedback capture | Implement thumbs up down and comment logging | Sprint 5
Epic | EPIC-05 Test & Stabilization | Test and stabilize | Validate data retrieval performance citations and user flows | Sprint 6
Story | EPIC-05 Test & Stabilization | Validate data coverage | Validate coverage per court language and citation accuracy | Sprint 6
Story | EPIC-05 Test & Stabilization | Functional testing | Test in-scope out-of-scope queries and filters | Sprint 6
Story | EPIC-05 Test & Stabilization | Performance testing | Validate indexing time query latency and error rates | Sprint 6
Story | EPIC-05 Test & Stabilization | Tuning and fixes | Adjust chunking prompts retries and thresholds | Sprint 6
Epic | EPIC-06 Deployment & Soft Launch | Deploy and launch | UAT deployment documentation and monitoring | Sprint 6
Story | EPIC-06 Deployment & Soft Launch | UAT deployment | Deploy jurisprudence content to EVA DA UAT | Sprint 6
Story | EPIC-06 Deployment & Soft Launch | Produce runbook | Document extraction operations re-runs and exceptions | Sprint 6
Story | EPIC-06 Deployment & Soft Launch | Soft launch monitoring | Monitor usage review feedback and log issues | Sprint 6

## ADO Sprints
Sprint | Sprint Dates (Indicative) | Phase | WBS ID | Task Name | Primary Outcome
Sprint 1 | Weeks 1-2 | Discovery | 1.1 | Business and Scope Alignment | Confirmed in-scope courts languages exclusions and success criteria
Sprint 1 | Weeks 1-2 | Discovery | 1.2 | Scope Validation | Confirm feature differentiation between EVA DA and Jurisprudence
Sprint 1 | Weeks 1-2 | Discovery | 1.3 | Source and Data Discovery | Validated CanLII API usage court access patterns and data risks
Sprint 1 | Weeks 1-2 | Discovery | 1.4 | EVA DA Constraints Review | Confirmed EVA DA ingestion indexing filtering and UI constraints
Sprint 2 | Weeks 3-4 | Discovery | 1.5 | Governance and Security Alignment | Confirmed public data posture logging and no new SAA boundary
Sprint 2 | Weeks 3-4 | Design | 2.1 | Extraction Design | CDC download retry and exception handling design approved
Sprint 2 | Weeks 3-4 | Design | 2.2 | Metadata and Storage Design | Metadata schema and storage contract finalized
Sprint 3 | Weeks 5-6 | Design | 2.3 | EVA DA Configuration Design | Index definitions chunking strategy and filters designed
Sprint 3 | Weeks 5-6 | Design | 2.4 | Prompt and UX Design | Scope citation and feedback prompts finalized
Sprint 4 | Weeks 7-8 | Investigation | 3.1 | CDC Job Implementation | Working CDC job detecting new and updated cases
Sprint 4 | Weeks 7-8 | Development | 3.2 | Document Downloader | Resilient EN FR document downloader implemented
Sprint 4 | Weeks 7-8 | Development | 3.3 | Metadata Generator | Metadata generation producing citation-ready fields
Sprint 5 | Weeks 9-10 | Development | 3.4 | Storage Setup | Ingestable storage structure ready for EVA DA
Sprint 5 | Weeks 9-10 | Development | 3.5 | EVA DA Index Creation | EN and FR jurisprudence indexes created
Sprint 5 | Weeks 9-10 | Development | 3.6 | Indexer Configuration | Indexers chunking and embeddings operational
Sprint 5 | Weeks 9-10 | Development | 3.7 | Filters Implementation | Court and language filters functional
Sprint 6 | Weeks 11-12 | Test | 4.1 | Data Validation | Validated coverage language correctness and citations
Sprint 6 | Weeks 11-12 | Test | 4.2 | Functional Testing | Verified in-scope out-of-scope queries and filters
Sprint 6 | Weeks 11-12 | Test | 4.3 | Performance Testing | Indexing latency and query performance validated
Sprint 6 | Weeks 11-12 | Test | 4.4 | Tuning and Fixes | Chunking prompt and retry tuning completed
Sprint 6 | Weeks 11-12 | Deployment | 5.1 | UAT Deployment | EVA DA UAT enabled with jurisprudence content
Sprint 6 | Weeks 11-12 | Deployment | 5.2 | Documentation and Runbook | Extraction and ops runbook delivered
Sprint 6 | Weeks 11-12 | Deployment | 5.3 | Soft Launch Monitoring | Usage monitored and initial feedback captured
Sprint intent (plain English)
Sprint 1 – Understand reality
Lock scope, confirm sources, avoid rework later.
Sprint 2 – Make it design-ready
CDC, metadata, storage, governance all nailed down.
Sprint 3 – Make EVA DA ready
Index strategy, prompts, filters defined before coding.
Sprint 4 – Build the extraction spine
CDC + downloader + metadata = foundation.
Sprint 5 – Connect to EVA DA
Indexes, ingestion, filters, citations working end-to-end.
Sprint 6 – Stabilize and launch
Test, tune, deploy, monitor — no heroics.

## Story points vs capacity
Issue Type | Epic Name | Summary | Description | Sprint | Story Points | Predecessor(s)
Epic | EPIC-01 Discovery & Alignment | Discovery and Alignment | Lock scope sources governance and EVA DA constraints for jurisprudence integration | Sprint 1
Story | EPIC-01 Discovery & Alignment | Confirm scope and success criteria | Confirm in-scope courts languages exclusions and definition of done | Sprint 1 | 5
Story | EPIC-01 Discovery & Alignment | Validate jurisprudence sources and access | Validate CanLII API usage court site access patterns and rate limits | Sprint 1 | 8 | Confirm scope and success criteria
Story | EPIC-01 Discovery & Alignment | Assess data quality risks | Identify unparsable PDFs missing bilingual pairs and document risks | Sprint 1 | 5 | Validate jurisprudence sources and access
Story | EPIC-01 Discovery & Alignment | Confirm EVA DA constraints | Confirm ingestion indexing filtering citation and UI constraints in EVA DA | Sprint 1 | 8 | Confirm scope and success criteria
Story | EPIC-01 Discovery & Alignment | Confirm governance posture | Confirm public data classification logging retention and no new SAA boundary | Sprint 2 | 5 | Confirm scope and success criteria
Epic | EPIC-02 Design Extraction & Metadata | Design extraction and metadata | Produce build-ready designs for CDC extraction metadata storage and prompts | Sprint 2
Story | EPIC-02 Design Extraction & Metadata | Design CDC strategy | Define change detection logic timestamps identifiers and run frequency | Sprint 2 | 8 | Confirm governance posture
Story | EPIC-02 Design Extraction & Metadata | Design download strategy | Define PDF HTML download retries backoff and exception handling | Sprint 2 | 5 | Design CDC strategy
Story | EPIC-02 Design Extraction & Metadata | Define metadata schema | Define case court language dates URLs and citation fields | Sprint 2 | 8 | Assess data quality risks
Story | EPIC-02 Design Extraction & Metadata | Define storage contract | Define folder structure naming conventions and overwrite rules | Sprint 2 | 5 | Define metadata schema
Story | EPIC-02 Design Extraction & Metadata | Design EVA DA indexes | Define EN FR index strategy chunking and filters | Sprint 3 | 8 | Confirm EVA DA constraints
Story | EPIC-02 Design Extraction & Metadata | Design prompts and UX rules | Define scope enforcement citation enforcement and feedback wording | Sprint 3 | 5 | Design EVA DA indexes
Epic | EPIC-03 Build Extraction Pipeline | Build extraction pipeline | Implement CDC downloader metadata generation and storage | Sprint 4
Story | EPIC-03 Build Extraction Pipeline | Implement CDC job | Build scheduled job to detect new and updated cases via CanLII | Sprint 4 | 8 | Design CDC strategy
Story | EPIC-03 Build Extraction Pipeline | Implement document downloader | Build resilient EN FR downloader with retries and logging | Sprint 4 | 8 | Design download strategy
Story | EPIC-03 Build Extraction Pipeline | Implement metadata generator | Generate structured metadata enabling filters and citations | Sprint 4 | 8 | Define metadata schema
Story | EPIC-03 Build Extraction Pipeline | Provision storage paths | Create ingestable storage structure for raw docs and metadata | Sprint 4 | 6 | Define storage contract
Epic | EPIC-04 EVA DA Configuration & Integration | Configure EVA DA | Create indexes configure ingestion filters citations and feedback | Sprint 5
Story | EPIC-04 EVA DA Configuration & Integration | Create jurisprudence project | Create EVA DA project space for EI Jurisprudence | Sprint 5 | 3 | Design EVA DA indexes
Story | EPIC-04 EVA DA Configuration & Integration | Create EN FR indexes | Create and validate jurisprudence EN and FR indexes | Sprint 5 | 5 | Create jurisprudence project
Story | EPIC-04 EVA DA Configuration & Integration | Configure indexers | Configure indexers chunking and embeddings | Sprint 5 | 8 | Provision storage paths
Story | EPIC-04 EVA DA Configuration & Integration | Enable court filters | Implement court and language filters using metadata | Sprint 5 | 5 | Implement metadata generator
Story | EPIC-04 EVA DA Configuration & Integration | Enforce citations | Ensure citation metadata is passed and enforced in prompts | Sprint 5 | 5 | Design prompts and UX rules
Story | EPIC-04 EVA DA Configuration & Integration | Enable feedback capture | Implement thumbs up down and comment logging | Sprint 5 | 5 | Design prompts and UX rules
Epic | EPIC-05 Test & Stabilization | Test and stabilize | Validate data retrieval performance citations and user flows | Sprint 6
Story | EPIC-05 Test & Stabilization | Validate data coverage | Validate coverage per court language and citation accuracy | Sprint 6 | 8 | Configure indexers
Story | EPIC-05 Test & Stabilization | Functional testing | Test in-scope out-of-scope queries and filters | Sprint 6 | 8 | Enable court filters
Story | EPIC-05 Test & Stabilization | Performance testing | Validate indexing time query latency and error rates | Sprint 6 | 5 | Configure indexers
Story | EPIC-05 Test & Stabilization | Tuning and fixes | Adjust chunking prompts retries and thresholds | Sprint 6 | 5 | Functional testing
Epic | EPIC-06 Deployment & Soft Launch | Deploy and launch | UAT deployment documentation and monitoring | Sprint 6
Story | EPIC-06 Deployment & Soft Launch | UAT deployment | Deploy jurisprudence content to EVA DA UAT | Sprint 6 | 5 | Validate data coverage
Story | EPIC-06 Deployment & Soft Launch | Produce solution architecture design document | Document extraction operations re-runs and exceptions | Sprint 6 | 3 | Implement CDC job
Story | EPIC-06 Deployment & Soft Launch | Soft launch monitoring | Monitor usage review feedback and log issues | Sprint 6 | 3 | UAT deployment

## WBS
Canonical Project WBS Table (Authoritative)
| WBS ID | Phase | Week Range | Task Name | Description | Primary Owner | Deliverable | Column1
4259 | 1.1 | Discovery | Weeks 1–2 | Scope Definition | Confirm in-scope courts languages exclusions(outside of EI-Jurisprudence) and definition of done | Product Owner | Approved scope statement
| 1.2 | Discovery | Weeks 1-2 | Scope Validation | Compare Feature sets in EVA DA vs Jurisprudence | Technical Lead | Confirm feature differentiation between EVA DA and Jurisprudence
4194 | 1.3 | Discovery | Weeks 1–2 | Source Validation | Validate CanLII API and court site access patterns limits and availability | Technical Lead | Source access validation report | CanLII api only gives metadata and not the pdfs. Contact Can LII to see if there is an MOU with ESDC to obtain access to api
4253 | 1.4 | Discovery | Weeks 1–2 | Data Quality Assessment | Identify unparsable PDFs missing bilingual pairs and inconsistencies | Data Lead | Data quality risk register | Identify bilingual documents and parse to have an English and French document
4254, 4255, 4526, 4257 | 1.5 | Discovery | Weeks 1–2 | EVA DA Capability Assessment | Confirm ingestion indexing filtering citation and UI constraints | Platform Architect | Platform fit assessment
4252 | 1.6 | Discovery | Weeks 1–2 | Target State | Test plans and acceptance criteria for Feature sign off
4251 | 1.7 | Discovery | Weeks 1–2 | Data Ingestion - Storage | Obtain the scrape of data used for the knowledge repository of Jurisprudence
| 2.1 | Design | Weeks 3–4 | CDC Design | Design change detection strategy timestamps identifiers and refresh cadence | Technical Lead | CDC design specification
| 2.2 | Design | Weeks 3–4 | Download Strategy Design | Design PDF HTML retrieval retries backoff and error handling | Technical Lead | Download strategy design
| 2.3 | Design | Weeks 3–4 | Metadata Schema Design | Define metadata required for filtering citations and traceability | Data Architect | Metadata schema definition
| 2.4 | Design | Weeks 3–4 | Storage Contract Design | Define folder structure naming conventions and overwrite rules | Platform Architect | Storage contract specification
| 2.5 | Design | Weeks 3-4 | Design Semantic Search Feature | Design and start coding for semantic search | Engineering Lead | Semantic Search design completed and reviewed
| 2.6 | Design | Weeks 3-4 | Data Ingestion : Part 2 | Query and Summary design to replicate current ingestion patter | Data Architect | Retrieval of summary and query data from initial scrape of Jurisprudence data
| 2.7 | Design | Weeks 5–6 | EVA DA Index Design | Define EN FR indexes chunking strategy filters and fields | Platform Architect | Index design document | De-listed since there is currently a French and English indexing structure in place.
| 2.8 | Design | Weeks 5–6 | Prompt and UX Design | Define scope enforcement citation enforcement and feedback wording | UX / AI Lead | Prompt and UX design spec
| 3.1 | Build | Weeks 7–8 | CDC Job Implementation | Implement scheduled job detecting new and updated cases | Engineering Lead | CDC job code and logs
| 3.2 | Build | Weeks 7–8 | Document Downloader Implementation | Implement resilient EN FR PDF HTML downloader | Engineering Lead | Downloader service
| 3.3 | Build | Weeks 7–8 | Metadata Generation Implementation | Generate structured metadata for each document | Engineering Lead | Metadata generation module
| 3.4 | Build | Weeks 7–8 | Storage Provisioning | Provision ingestable storage paths and access controls | Platform Ops | Provisioned storage structure
| 4.1 | Integration | Weeks 9–10 | Project Space Creation | Create EVA DA project space for EI Jurisprudence | Platform Ops | EVA DA project space
| 4.2 | Integration | Weeks 9–10 | Index Creation | Create and configure EN and FR jurisprudence indexes | Platform Ops | Configured search indexes
| 4.3 | Integration | Weeks 9–10 | Indexer Configuration | Configure indexers chunking embeddings and schedules | Platform Ops | Operational indexers
| 4.4 | Integration | Weeks 9–10 | Filter Enablement | Enable court and language filters using metadata | Application Lead | Working filters
| 4.5 | Integration | Weeks 9–10 | Citation Enforcement | Ensure citation metadata is passed and enforced in responses | AI Lead | Citation-enabled responses
| 4.6 | Integration | Weeks 9–10 | Feedback Capture Enablement | Enable thumbs up down and comment logging | Application Lead | Feedback capture mechanism
| 5.1 | Test | Weeks 11–12 | Data Validation | Validate coverage per court language and citation accuracy | QA Lead | Data validation report
| 5.2 | Test | Weeks 11–12 | Functional Testing | Test in-scope out-of-scope behavior filters and UX | QA Lead | Functional test results
| 5.3 | Test | Weeks 11–12 | Performance Testing | Validate indexing time query latency and error rates | QA Lead | Performance benchmark report
| 5.4 | Test | Weeks 11–12 | Tuning and Remediation | Adjust chunking prompts retries thresholds | Engineering Lead | Tuned configuration
| 6.1 | Deployment | Weeks 11–12 | UAT Deployment | Deploy jurisprudence capability to EVA DA UAT | Release Manager | UAT deployment completed
| 6.2 | Deployment | Weeks 11–12 | Operational Runbook | Document extraction re-runs exceptions and support model | Operations Lead | Approved runbook
| 6.3 | Deployment | Weeks 11–12 | Soft Launch Monitoring | Monitor usage review feedback and capture backlog | Product Owner | Post-launch monitoring report