## Features
Epic | Feature Name | Feature Description | Component Affected | Responsible | ETA | Design Status | Implementation Status
Web Application | Web Branding | Apply all ESDC theme and branding to the web application | frontend web application |  |  | Complete | Complete
Web Application | Web mockup | Define and desgin the web mockup for the web application. The application should have 5sections: chat area, configuration area, filter area, flow process, citations | frontend web application | Application |  | Complete | Complete
Web Application | Web page authentication | integrate the web application with the Active directory for SSO | frontend web application | Application |  | Complete | Complete
Web Application | Web page authorization | implement authorization with AD Group. Define a group to use the application ex: AD_JURIS_WEBUSER | frontend web application | Application |  | Complete | Complete
Web Application | Web filters | implement filters for the web application. These filters could be dropdown, option box or multi selection checkbox; Dropdowns / checkboxes for: Court hierarchy (SCC, FCA, FC, SST, etc.) Date ranges Case categories (EI vs CPP vs Other) Language (EN/FR) ; Parking Lot (Denial vs Approval) | frontend web application | Application |  | Complete | Complete
Web Application | Web Enhancement - Hierarchy | Court hierarchy-based browsing view (tree / dropdown) | frontend web application | Application |  | Complete | Complete
Web Application | Web Enhancement - Case Numbers | Display case numbers in UI results. | frontend web application | Application |  | Complete | Complete
Web Application | Web Enhancement - French Landing Page | French landing page by default (with toggle) ; Manual Toggling vs Automated toggling | frontend web application | Application |  | Complete | Complete
Web Application | Web Enhancement - Feedback Management | Feedback Functionality (categories as well as free text input) | frontend web application | Application |  | Complete | Complete
Web Application | Accessibility | Accessibility Features i.e readability, screen reading/scraping |  |  |  | Complete | Complete
infrastructure | Infrastructure as Code (terraform) |  |  |  |  | Complete | Complete
infrastructure | Azure DevOps foundation | setup azure DevOps and provide user acces to the team | Sandbox environment | Infra/Security |  | Complete | Complete
infrastructure | Azure DevOps Git Repo | Create all Git repository for the project | Sandbox environment | Infra/Security
infrastructure | OpenAi Block Infra | provision and configuration of the infrastructure and network components for the block. Connectivity to OpenAI service endpoint. | Sandbox environment | Infra/Security |  | Complete | Complete
infrastructure | GenAi Block Infra | provision and configuration of the infrastructure and network components for the block. LLM orchestration + prompt layer | Sandbox environment | Infra/Security |  | Complete | Complete
infrastructure | Application Block Infra | provision and configuration of the infrastructure and network components for the block. APIs, App Service hosting.App Insights, Log Analytics. | Sandbox environment | Infra/Security |  | Complete | Complete
infrastructure | Logging and monitoring | provision and configuration of the infrastructure and network components for the monitoring and logging of the solution components | Sandbox environment |  |  | Complete | Complete
Security | OpenAi Block Security | configuration and review of the Security (AD Groups, network security, access control) for the block. | Sandbox environment | Security |  | Complete | Complete
Security | GenAi Block Security | configuration and review of the Security (AD Groups, network security, access control) for the block | Sandbox environment | Security |  | Complete | Complete
Security | Application Block Security | configuration and review of the Security (AD Groups, network security, access control) for the block | Sandbox environment | Security |  | Complete | Complete
Security | Data Security | configuration and review of the Security (AD Groups, network security, access control) for the data stored in the Data repository : Encrypt data at rest (CosmosDB / Blob / ADLS,), Data Pipeline: Encrypt data in transit | Sandbox environment | Security |  | Complete | Complete
Backend | Backend authentication | integrate the web application with the Active directory for SSO (Mirror AD integration from front-end for APIs) | backend web application | Application |  | Complete | Complete
Backend | Backend authorization | implement authorization with AD Group. Define a group to use the application ex: AD_JURIS_WEBUSER | backend web application | Application |  | Complete | Complete
Backend | Prompt filters (Merge 26 & 27) | Implement filters parameter for the web application. These filters could be dropdown, option box or multi selection checkbox . | backend web application | Application |  | Complete | Complete
Backend | Topic Relevant Filtering | design and implement the feature . Topic relevance filtering (e.g., EI vs CPP vs Immigration). | backend web application | Data Science/Application |  | Complete | Complete
Backend | PII Filter | design and implement the feature. PII Filter to block sensitive names/numbers. | backend web application | Data Science/Application |  | Complete | Complete
Backend | Language Detection (29, 30, 31 associated) | design and implement the feature.Language Detection → auto-surface correct EN/FR decision. | backend web application | Data Science/Application |  | Complete | Complete
Backend | Index Selection | design and implement the feature : Index Selection → choose SCC, FCA, FC, SST indexes. | backend web application | Data Science/Application |  | Complete | Complete
Backend | Query Search Creation | design and implement the feature : Index Selection → choose SCC, FCA, FC, SST indexes. | backend web application | Data Science/Application |  | Complete | Complete
Backend | Response Creation ( Circle back) | design and implement the feature. Query creation with prompt templates. Response generation + citation grounding. | backend web application | Data Science/Application |  | Complete | Complete
Backend | History Management | design and implement the feature: History Management – store per-user chat logs; Feedback management | backend web application | Data Science/Application |  | Complete | Complete
Backend | Feedback Management |  |  |  |  | Complete | Complete
data pipeline | data scrapping | Desing and implement the data scrapping for the data sources ( 3 from PoC and 1 additional - double check ). Design should include: - metadata - source to text(pdf) - data structure, classification (court level, decision type, EI Flag), source and categorization, IsAvailableinFrench vs English | data pipeline | Data Engineer |  | Complete | Complete
data pipeline | Vectorization | Create vectors (index) | data pipeline | Data Engineer |  | Complete | Complete
data pipeline | Delta ingestion | orchestrate data scrapping and index creation with delta pulls based on most recent information ; If a case is updated, is there a new document updated or just an addendum | data pipeline |  |  | Complete | Complete
data pipeline | Feedback Management | feedback management |  |  |  | Complete | Complete
data pipeline | History Management | history management |  |  |  | Complete | Complete
Prompt Engineering | Prompt Enhancements | Prompt enhancements (context injection, bilingual prompt chaining, inference for change in documents/cases) |  |  |  | Complete | Complete
Prompt Engineering | Open AI Model Refresh | OpenAI model refresh (new versions plugged without re-architecture). |  |  |  | Complete | Complete

## SprintWiseDeliverables
[5 empty] | Debbie | Paula | Lucy Lu | Debbie
Sprint | Week | Dates | Depenedency | Focus | Data Engineering | Prompt Engineering | Front End Development | Backend Development
Sprint 0 & 1 (Pre-Oct 6) | Week 0 - Week 3 | Sep 15 - Oct 3 |  | ADO/Git setup, infra prep
Sprint 2 (Oct 6 – mid-Oct) | Week 4- Week 5 | Oct 6 - Oct 17 |  | UI branding + mockups, AuthN setup, initial prompt work |  | Prompt enhancements, retrieval quality definition. | Week 5–6: Backend authentication & authorization. | Backend authentication & authorization.
Sprint 3 (Late Oct – Nov) | Week 6- Week 7 | Oct 20 - Oct 31 | Dev Env Creation (Data factory) - Accenture | data pipleine development (data scraping for new source starts) Backend filters, authorization, prompt enhancements, EN/FR detection, Fench Landing Page , Accessibility (ESDC), APIM Instance (ESDC) | Data Pipeline Creation - Data scraping, vectorization setup | Retrieval quality definition, Align prompt patterns with backend filters & data. | Filters (prompt + topic relevant), language detection, PII filters, Index selection, query creation, response creation | Filters (prompt + topic relevant), language detection, PII filters
Sprint 4 (Nov – mid Nov) | Week 8- Week 9 | Nov 3 - Nov 14 |  | UI hierarchy & case #, response generation, vectorization, model refresh | Data Pipeline Creation coninues, Delta ingestion pipeline, feedback loop integration, Data history management | OpenAI model refresh, tuning with adjudicator feedback. | History management, backend feedback logging | Index selection, query creation, response creation
Sprint 5 ( mid Nov-Dec) | Week 10 - Week 11 | Nov 17 - Nov 28 |  | Feedback management, delta ingestion, French landing page, feedback UI , Accessibility Testing & Compliance | Feedback Loop & History management continues with data persistence | Hierrachy Development | Accessibility Feature Development | History management, backend feedback logging.
Sprint 6 (Dec - mid Dec ) | Week 12- Week 13 | Dec 1- Dec 12 |  | Chat History Management, ,Logging (Backend), Accessibility Testing & Compliance | End-to-end integration with backend & UI | Hierrachy tuning with adjudicator feedback | Integration testing with UI + data pipeline | Integration testing with UI + data pipeline.
Sprint 7 (Late Dec – Jan) | Week 14- Week 15 | Dec 15 - Dec 26 |  | User Testing & User Testing Support + Code Fix & Testing , KT | Data validation during UAT, UAT Support, KT | UAT Support, Feedback incorporation, KT | UAT Support, Feedback incorporation, KT | UAT Support, Feedback incorporation, KT
Sprint 8 (Jan – mid Jan) | Week 16- Week 17 | Dec 29 - Jan 9

## Feature-Story Mapping
Feature Story Mapping | This sheet will be maintained only for Epic-->Feature-->Story--> Task mapping; Story Definition, Acceptance criteria, Design Links are just to give the example and will be maintained in the ADO not in the excel
Epic | Feature | Story | Sprint | Story Definition | Acceptance Criteria | Notes/updates
Web Application | Web Branding | Apply All ESDC Theme and Branding – Gather ESDC Branding Guidelines | Sprint 2 | As a front-end developer, I want to collect and review the official ESDC branding guidelines, design system assets so that I can apply the approved ESDC theme (look, feel, branding) consistently across the web application. | • Official ESDC UI/UX design system and branding documentation (e.g., colors, fonts, logos, layout templates) are located and reviewed • A reference document (Wiki page) is created summarizing the branding guidelines for the dev team • A Wiki page reflecting the wireframe for the front end • Approval on Wireframes from BDM Innovation and AICOE is obtained before implementation start | done
Web Application | Web Mockup | Define and design mockups | Sprint 2 | As a UX designer, I want to define wireframes and mockups so that developers can implement consistent UI layouts and interactions. | • Core pages wireframed (landing, search, results) • Mockups reviewed with business stakeholders • Approved EN & FR mockups handed off to dev team | done
Web Application | Accessibility | Accessibility compliance WCAG 2.1 | Sprint 3-5 ( ESDC) | As a public-facing web application user (including users with disabilities), I want the application to comply with WCAG 2.1 Level AA accessibility standards, so that I can access and use all core functionalities without barriers, regardless of my assistive technologies. | N/A
Web Application | Web Page Authentication | Integrate AD SSO | Sprint 3 | As a user, I want to sign in using AD SSO so that my access is secure and seamless. | • Azure AD app registration configured • Backend OAuth/OpenID flow implemented • Frontend integrated with SSO flow • End-to-end authentication validated | Group created, security tested
Web Application | Web Page Authorization | Implement AD Group authorization | Sprint 3 | As an administrator, I want to restrict access based on AD groups so that different user roles have appropriate permissions. | • AD groups created and mapped to roles • Backend role-based access implemented • UI elements secured per role • Authorization tested with multiple roles | Group created, security tested
Web Application | English Landing Page | Develop English Landing page in EVA DA | Sprint 3 | As an adjudicator or legal researcher, I want to filter search results by court, date, category, and language, so that I can quickly narrow down relevant case law and access the most pertinent decisions for my query. | Filter selections must persist when navigating between result pages. Filtering should not require a full page reload (preferably async refresh). Default state = no filters applied → full result set.
Web Application | Web Filters | Filtering on court | Sprint 3 | As an adjudicator, I want to filter search results by court, date, category, and language so that I can efficiently find relevant cases. | • Filter UI components implemented • Backend filtering API integrated • Court/date/category/language filters functional • End-to-end filtering validated
Data Engineering | Web Filters | Filtering on court | Sprint 4 | As an adjudicator, I want to filter search results by court, so that I can efficiently find relevant cases. | TBD | KG added to ADO OCt c9 Debbie updated Oct 29
Data Engineering | Web Enhancement - Case Numbers | Display case numbers | Sprint 4 | As an adjudicator, I want case numbers displayed in search results so that I can quickly identify relevant cases. | • Case numbers surfaced in search API, source data URL • Displayed in result cards • Bilingual display validated | Switched to Data Engineering by KG Oct 29 Assigned to Debbie
Web Application | Web Enhancement - French Landing Page | French landing page default + toggle | Sprint 3–4 | As a user, I want the landing page to default to French with a toggle so that the app complies with bilingual standards. | • French toggle implemented • FR landing page content localized • Accessibility check for toggle passed
Backend | Web Enhancement - Hierarchy | Court hierarchy browsing | Sprint 5 | As an adjudicator, I want to browse decisions by court hierarchy so that I can navigate efficiently. | • Court hierarchy data fetched from index • Facet tree implemented in UI • Keyboard navigation and accessibility supported • Filter interaction validated | (changed from web app to backend) assign to Paola) KG updated user story Oct 29: assigned to Paola
Web Application | Web Enhancement - Feedback Management | Feedback buttons | Sprint 5 | As a user, I want to provide quick feedback (thumbs up/down) so that the team can continuously improve response quality. | • Feedback buttons added to UI • Events captured and stored in backend • Feedback tied to query/session metadata • Analytics integration validated | Feeback implemented but updated to category based feedback as well as freeform text capability. Data flowing to Cosmos DB and available for analysis
Backend | Backend Authentication | Integrate backend with AD SSO | Sprint 2–3 | As a backend developer, I want to integrate the backend with AD SSO so that users can securely log in using their organizational credentials. | • Azure AD app registration completed • OAuth2/OpenID middleware implemented • Token validation logic in backend • End-to-end login flow tested
Backend | Backend Authorization | Backend AD Group authorization | Sprint 3 | As a backend developer, I want to implement AD group-based authorization so that only users with appropriate roles can access specific resources. | • AD group roles mapped to backend • Role-based middleware created • Access control applied to endpoints • Tested with multiple roles
Backend | Prompt Filters | Implement filter params in backend | Sprint 5 | As a backend developer, I want to implement prompt and query filter parameters so that the chatbot can retrieve more accurate and relevant results. | • Filter params parsed and validated • Integrated with retrieval logic • Unit tests for filter combinations • End-to-end filtering validated | KG updated to owner: Paola (updated to sprint 5) on oct 29
Backend (change to prompt engineering) | Topic Relevant Filtering | Topic filtering by EI | Sprint 3 | As a backend developer, I want to implement topic filtering (EI) so that users can restrict responses to relevant program areas. Irrelevant Questions to yield a response marking "irrelevant question" | • Topic filters integrated into query builder • EI tags supported • API returns filtered results accurately • Edge cases tested | assign to Paola
Backend | PII Filter | Block sensitive names/numbers | Sprint 6 | As a backend developer, I want to implement a PII filter so that sensitive information like names and numbers is not returned in responses and are not captured in chat history | • PII patterns defined validated • Filter applied to prompts and responses • Logs contain masked values • Security review completed
Backend | Language Detection | Detect EN/FR automatically | Sprint 3 | As a backend developer, I want to detect whether the query is in English or French so that the correct index can be queried. | • Language detection model integrated • Automatic routing to EN/FR indexes • Detection accuracy validated with sample queries • Error handling for unknown inputs
Backend | Response Creation | Query creation with templates | Sprint 3 | As a backend developer, I want to build query templates so that search requests are consistently structured for the retrieval engine. | • Query template created • Variables parameterized • Templates integrated into search API • Tests for various query scenarios
Backend | History Management | Store user chat logs | Sprint 5 | As a backend developer, I want to store user chat logs securely so that the system can support chat history and auditability. | • Chat log schema designed • Storage and retrieval APIs implemented • Data retention policies applied • Logs encrypted and tested
Backend | App selection | Enable Jurisprudence app based on user group | Sprint 3 | As a backend developer, I want to make sure I can access the jurisprudence app if I'm an authorised user | • User is able to access Jurisprudence in english is project 49 selected • Useris able to access Jurispruence in French is Project 50 is selected | no longer valid after switch to ABRG
Data Pipeline | Data Scraping | Ingest PoC + new sources | Sprint 3 | As a data engineer, I want to set up a robust data scraping pipeline that ingests both PoC and newly identified data sources, so that relevant case law and legal content can be automatically collected, standardized, and indexed for downstream processing. | • PoC source endpoints successfully ingested • New sources added and parsed in standardized format • Error handling and logs implemented
Data Pipeline | Vectorization | Create vector indexes | Sprint 4 | As a data engineer, I want to vectorize ingested legal content and store vector embeddings in indexes, so that the application can perform semantic search and retrieval efficiently. | • Embeddings generated for all ingested documents • Vector indexes created and populated • Bilingual embeddings stored with proper metadata
Data Pipeline | Delta Ingestion | Delta pull of updated cases | Sprint 3 | As a data engineer, I want the ingestion pipeline to support delta pulls, so that only newly added or updated cases are fetched and indexed, reducing redundancy and load. | • Incremental detection based on timestamps • Deduplication implemented for previously ingested data • Scheduled delta runs executed with proper logging • No duplicate records created
Data Pipeline | Feedback Management | Pipeline to process feedback | Sprint 5 | As a data engineer, I want a pipeline that processes user feedback (thumbs up/down, corrections, relevancy signals), so that this data can be stored and used for future model improvements and content updates. | • Feedback events ingested and stored in structured format • Invalid records logged and skipped • Secure storage with metadata (user ID, query ID, timestamps)
Data Pipeline | History Management | Pipeline to store history | Sprint 5 | As a data engineer, I want to develop pipeline to store user query and interaction history, so that past interactions can be used for audits, personalization, and analytics. | • Queries, responses, and metadata stored • Encrypted storage of sensitive identifiers • Queryable history for analytics and audits
Prompt Engineering | Response Creation | Enhance prompts for answer generation | Sprint 3 | As a backend developer, I want to generate structured responses with citations so that users receive grounded and traceable answers. | • ensure answer contains: - summary, decision, date, case name court name and citations
Prompt Engineering | OpenAI Model Refresh | Refresh OpenAI model without re-architecture | Sprint 3 | As a prompt engineer, I want to refresh the underlying OpenAI model without changing the overall architecture, so that the system benefits from updated model capabilities with minimal disruption. | • Model configuration updated to new version without code refactoring | completed already
Infrastructure | Infratsructure as Code | Bicep Code Analysis | Sprint 2 | As a cloud engineer, I want to analyze existing Bicep templates used in the PoC environments, so that I can understand current infrastructure components, identify reusable elements, and inform the Terraform target architecture. | • Existing Bicep templates reviewed for OpenAI, GenAI, and Application blocks • Components documented (RGs, VNets, subnets, NSGs, App Services, etc.) • Reusable patterns and environment-specific differences identified • Gaps and refactoring considerations captured in Confluence / design doc
Infrastructure | Infratsructure as Code | Create Target Repository Structure (Terraform) | Sprint 2 | As a cloud engineer, I want to define and implement the target Terraform repository structure, so that the infrastructure codebase follows a modular, scalable, and maintainable structure aligned with enterprise standards. | • Repository structure defined for core modules, environment folders, and pipelines • Folder hierarchy created in the designated repo • Naming conventions and backend configuration documented • Structure reviewed and approved by architecture/security teams
Infrastructure | Infratsructure as Code | Identify Remote State Strategy & Environment Isolation | Sprint 2 | As a cloud engineer, I want to define the remote state management and environment isolation strategy for Terraform, so that multiple teams can collaborate safely and deploy infra consistently across environments. | • Remote state backend selected (e.g., Azure Storage with state locking) • Environment isolation strategy documented (e.g., separate state files per env) • Strategy reviewed and approved by cloud governance team
Infrastructure | Infratsructure as Code | Create Infratsructure as Code (Terraform) | Sprint 2 | As a cloud engineer, I want to implement the infrastructure as Terraform code using the defined structure, so that infrastructure can be provisioned in a consistent, automated, and repeatable way across environments. | • Terraform modules created for core components (network, OpenAI, GenAI, App blocks, monitoring) • Environment-specific variables and configurations implemented • Terraform plan and apply executed successfully in at least one non-prod environment
Infrastructure | OpenAI Block Infra | Provision infra + connectivity to OpenAI | Sprint 2-3 | As a cloud engineer, I want to provision infrastructure and connectivity for the OpenAI block, so that the application can securely and reliably connect to the OpenAI service for inference. | • Required RGs, VNets, subnets, NSGs provisioned • Private endpoints or firewall rules configured • Connectivity validated to OpenAI endpoints • IaC templates stored in repo | provisioned by AI COE KG updated Oct 30
Infrastructure | GenAI Block Infra | Provision infra + prompt layer | Sprint 1–2 | As a cloud engineer, I want to provision the GenAI block infrastructure including prompt orchestration layers, so that application components can interact with vector search and model APIs in a secure and scalable manner. | • GenAI RG, networking and services provisioned • Prompt orchestration layer deployed and accessible • Connectivity between GenAI block and OpenAI block validated • Terraform modules stored and versioned | provisioned by AI COE KG updated Oct 30
Infrastructure | Application Block Infra | Provision APIs and App Hosting | Sprint 3–4 | As a cloud engineer, I want to provision infrastructure for application hosting and APIs, so that the web app and backend services can be deployed and accessed securely. | • App Service or container hosting environment created • API Management or gateway configured (ESDC) • Infra IaC tested and stored in repo | Richard to update
Infrastructure | Logging & Monitoring | Enable monitoring & logging | Sprint 3–4 | As a DevOps engineer, I want to enable logging and monitoring across all blocks, so that operational issues can be detected and addressed quickly. | • App Insights / Log Analytics configured • Logs available for audit and troubleshooting | Richard to update
DevOps | Deploying IoC via pipeline | DevOps: Implement Stage to deploy Terraform IaC | Sprint 4 | As a cloud engineer/developer, I want to deploy infrastructure via a DevOps pipeline using Terraform, so that infrastructure can be provisioned in a consistent, automated, and repeatable way across environments. | •Implement logic in Deploy_Infrastructure2 stage to deploys the specified IaC components •Environment-specific variables and configurations implemented •Stage is executed successfully in at least one non-prod environment
Security | OpenAI Block Security | Secure OpenAI block | Sprint 3–4 | As a security engineer, I want to secure the OpenAI block infrastructure, so that only authorized services can access model endpoints. | • Network rules / private endpoints configured • Secrets stored in Key Vault • Access policies and managed identities applied • Security scan completed | covered in IaC
Security | GenAI Block Security | Secure GenAI block | Sprint 3–4 | As a security engineer, I want to secure the GenAI block infrastructure, so that prompt orchestration and vector services are protected from unauthorized access. | • Role-based access applied to services • Key Vault and MSI used for secrets • Firewall rules and NSGs configured • Threat modeling and basic pen-test completed
Security | Application Block Security | Secure application block | Sprint 3–4 | As a security engineer, I want to secure the application hosting environment, so that web and API services are protected from unauthorized access and meet compliance requirements. | • AD authentication & authorization configured • TLS/SSL enforced • App roles & policies applied • Security baseline scan passed
Security | Data Security | Data encryption and controls | Sprint 3–4 | As a security engineer, I want to ensure data encryption and controls are applied across pipelines and storage, so that sensitive data complies with PBMM and organizational security standards. | • Data encrypted at rest and in transit • Access controls applied to storage accounts • Audit logging enabled • Compliance checks documented
Testing | English Landing Page | Filtering on court | Sprint 3 | As a tester, I want to ensure that I am able to filter search results by court, date, category, and language | Filter selections must persist when navigating between result pages. Filtering should not require a full page reload (preferably async refresh). Default state = no filters applied → full result set.
Testing | Web Enhancement - Case Numbers | Display case numbers | Sprint 4 | As a tester, I want to ensure case numbers are displayed in search results so that I can quickly identify relevant cases. | • Case numbers surfaced in search API, source data URL • Displayed in result cards • Bilingual display validated
Testing | Web Enhancement - French Landing Page | French landing page default + toggle | Sprint 3–4 | As a user, I want the landing page to default to French with a toggle so that the app complies with bilingual standards. | • French toggle implemented • FR landing page content localized • Accessibility check for toggle passed
Testing | Web Enhancement - Hierarchy | Court hierarchy browsing | Sprint 5 | As a tester, I want to ensure I can browse decisions by court hierarchy so that I can navigate efficiently. | • Court hierarchy data fetched from index • Facet tree implemented in UI • Keyboard navigation and accessibility supported • Filter interaction validated
Testing | Web Enhancement - Feedback Management | Feedback buttons | Sprint 5 | As a tester, I want to ensure I can provide quick feedback (thumbs up/down) so that the team can continuously improve response quality. | • Feedback buttons added to UI • Events captured and stored in backend • Feedback tied to query/session metadata • Analytics integration validated
Testing | Prompt Filters | Implement filter params in backend | Sprint 5 | As a tester, I want to ensure functionality of prompt and query filter parameters so that the chatbot can retrieve more accurate and relevant results. | • Filter params parsed and validated • Integrated with retrieval logic • Unit tests for filter combinations • End-to-end filtering validated
Testing | Topic Relevant Filtering | Topic filtering by EI | Sprint 3 | As a tester, I want to ensure functionality of the topic filter so that users can restrict responses to relevant program areas. Irrelevant Questions to yield a response marking "irrelevant question" | • Topic filters integrated into query builder • EI tags supported • API returns filtered results accurately • Edge cases tested
Testing | PII Filter | Block sensitive names/numbers | Sprint 6 | As a tester, I want to ensure any PII is filtered so that sensitive information like names and numbers are not returned in responses and are not captured in chat history. | • PII patterns defined validated • Filter applied to prompts and responses • Logs contain masked values • Security review completed
Testing | Language Detection | Detect EN/FR automatically | Sprint 3 | As a tester, I want to ensure the chatbot can detect whether the query is in English or French so that the correct index can be queried. | • Language detection model integrated • Automatic routing to EN/FR indexes • Detection accuracy validated with sample queries • Error handling for unknown inputs
Testing | History Management | Store user chat logs | Sprint 5 | As a tester, I want to ensure user chat logs and chat history are stored. | • Chat log schema designed • Storage and retrieval APIs implemented • Data retention policies applied • Logs encrypted and tested
Testing | App selection | Enable Jurisprudence app based on user group | Sprint 3 | As a tester, I want to make sure I can access the jurisprudence app if I'm an authorised user. | • User is able to access Jurisprudence in english is project 49 selected • Useris able to access Jurispruence in French is Project 50 is selected
Testing | Data Scraping | Ingest PoC + new sources | Sprint 3 | As a tester, I want to ensure that the app can correctly identified data sources, so that relevant case law and legal content can be automatically collected, standardized, and indexed for downstream processing. | • PoC source endpoints successfully ingested • New sources added and parsed in standardized format • Error handling and logs implemented
Testing | Delta Ingestion | Delta pull of updated cases | Sprint 3 | As a tester, I want to ensure that the ingestion pipeline does not pull duplicate data. | • Incremental detection based on timestamps • Deduplication implemented for previously ingested data • Scheduled delta runs executed with proper logging • No duplicate records created
Testing | Feedback Management | Pipeline to process feedback | Sprint 5 | As a tester, I want user feedback (thumbs up/down, corrections, relevancy signals) to be stored. | • Feedback events ingested and stored in structured format • Invalid records logged and skipped • Secure storage with metadata (user ID, query ID, timestamps)

## Infrastructure Story to Task
Epic | Feature | Story | Story Definition (Ayushi to refine) | Tasks | Sequence
Infrastructure | Infratsructure as Code | Bicep Code Analysis | Understand scope, overlap, and compatibility issues before the creation of new terraform script. | • Used providers, versions [Identify which cloud providers and versions are used - POC might have been created by BICEP] • Backend configs [Review how Terraform stores its state (remote backend like Azure Storage, local files, etc.).] • Resource group naming, regions [Check how resource groups are named and which Azure regions (location) are used.] • Module usage patterns [Review how Terraform modules are structured and reused (local modules, remote modules, etc.).] • Any overlapping resources or naming collisions [Identify any resources that both codebases create with the same names or purposes.] | 1
Infrastructure | Infratsructure as Code | Create Target Repository Structure (Terraform) | Propose a clean, scalable repo structure for the new combined repo. | • Mono vs multi-env repo [Decide whether to keep all environments (dev, dev/test, UAT) in one repo (mono) or split them into separate repos.] • Naming conventions [Establish consistent naming rules] For: o Files and folders o Resource groups and resources (via Terraform name values) o Module naming, environment labels • Directory layout for Terraform [Decide how the Terraform files are structured in the repo.] | 2
Infrastructure | Infratsructure as Code | Identify Remote State Strategy & Environment Isolation | clear plan for backend storage and environment separation. | • One state file per environment (dev, prod, etc.) [Each environment (e.g., dev, test, prod) should have its own isolated Terraform state file.] • Azure Storage account config [Define the backend storage for Terraform state using an Azure Storage Account with a blob container.] • State key naming pattern [Define a consistent naming pattern for the key used in backend config — this is the "file name" of the state blob.] • State locking approach [Ensure state locking is enabled to prevent concurrent modifications] | 3
Infrastructure | Infratsructure as Code | Create Infratsructure as Code (Terraform) | Terraform Code | Write Terraform code equivalent to Bicep | 4

## Backlog
No. | Category ​ | Feature Name ​ | Description ​ | Notes ​
1​ | Filter ​ | Filter – Type ​ | Filter to add type (EI, CPP, OAS) to filter out the court Cases ; ​ | For beyond EI expansion ​
Note: Jurisprudence MVP to have only Court as a filter ​
2​ |  | Add Filtering Options – “Appeal Made By”​ | Add UI filters to allow users to filter decisions by the party appealing: Commission vs Claimant.​ | Legal team raised the requirement. Does not impact the accuracy or recovery but helps in discoverability​
3​ |  | Add Filtering Options – GD vs AD​ | Add a filter to distinguish between General Division (GD) and Appeal Division (AD) decisions ​ | Only Applicable for SST. Legal team raised this to be filter that will help them ​
4​ |  | Add Filtering Options – Dates​ | Add filtering capabilities by decision date or date range to refine search results.​ | Nice to have but chatbot can still do the same by asking bot to search within a time frame ​
“​ |  | Tag Umpire and Referee Decisions​ | Add explicit tagging or filters for Umpire” and “Referee” decisions to improve discoverability.​ | Appeal writers requested this to improve the recoverability. No discussion were led to understand further how to identify “Umpire” vs “Referee”​
6​ | Feedback ​ | Neutral Feedback ​ | Feedback that is neither positive or negative ​ Note: Aligning with AICOE , Jurisprudence MVP to have thumbs up and thumbs down feedback captured​ | AICOE & BDM Innovation raised this. ​
Sentiment Analysis is required for the neutral feedback ​
7​ |  | Multiple Feedbacks ​ | Ability to provide both positive and negative feedback and choosing two different negative/positive category at the same time ​ | SCBOs expressed the interest to have something for future. ​ Front end and backend ​
8​ | ​ | Feedback Response Suggestion ​ | Ability for auto suggesting a feedback response ​ | SCBOs expressed interest to have an auto-suggested feedback response​
9​ | Data Source & Refresh ​ | Switch SST → BOA for GD Decisions​ | Update data ingestion pipeline to reflect transition of EI General Division (GD) decisions from SST to Board Of Appeal(BOA). Older decisions remain in SST; AD decisions continue to reside on SST. The switch from SST to BOA to rake place sometime in 2026 ​ | JP MVP timeframe does not overlap with the timeframe of the transition ​
10​ |  | Increase Data Sources Update Frequency​ | Move from Weekly to at daily updates post the cost assessment ​ | Weekly memo/email that explain the key acts and regulations or decisions to be considered before making decisions on appeals and reconsiderations; however, it will be better to have daily updates if the costs and support impact is not high ​